# Study Closeout Checklist

Purpose: Confirms that participant, data, product, regulatory, financial and record tasks are complete before a study is closed at the site.

Instructions

When the sponsor announces end of enrollment or last participant last visit, the Lead CRC opens this checklist and enters an owner (initials) and target date for each item (SOP-15 5.1.1).

Enter the date each item is done. Mark N/A only with a reason in the comments.

Close the study with the IRB only when the IRB's closure criteria are met; while the sponsor is still sending queries, the study stays open unless the IRB says otherwise (SOP-15 5.7.1).

When all items are complete, the Lead CRC and PI sign and the Regulatory Coordinator files the checklist in the ISF. After archiving, the PI signs the archive-complete line and the checklist is filed with the archive record on F-402-01 (SOP-15 5.11.1).

| Protocol number |  | Sponsor |  |
| --- | --- | --- | --- |
| Site number |  | PI name |  |

## Participants (SOP-15 5.2)

| Item | Owner | Target | Done | N/A | Comment |
| --- | --- | --- | --- | --- | --- |
| End-of-study visits done and status in EDC |  |  |  |  |  |
| Ongoing care discussed and transfer of care documented where needed |  |  |  |  |  |
| Ongoing AE, SAE and pregnancy follow-up arranged (SOP-09) |  |  |  |  |  |
| Preferences for results and treatment information recorded; assignments received and participants told (blinded trials) |  |  |  |  |  |
| Results summary sent to participants who asked, after IRB approval where required |  |  |  |  |  |

## Data and specimens (SOP-15 5.3, 5.4)

| Item | Owner | Target | Done | N/A | Comment |
| --- | --- | --- | --- | --- | --- |
| All data entered, queries resolved, source reconciled with EDC |  |  |  |  |  |
| Investigator sign-off of casebooks completed |  |  |  |  |  |
| Copy of eCRF data with audit trail received and checked (opens, every participant) |  |  |  |  |  |
| Records obtained from other external systems (IRT, eCOA, portals, eConsent) |  |  |  |  |  |
| Specimens reconciled with sponsor receipts (F-311-01); remaining specimens handled per written instruction |  |  |  |  |  |
| Unused kits and supplies returned or destroyed as instructed |  |  |  |  |  |

## Investigational product and equipment (SOP-15 5.4)

| Item | Owner | Target | Done | N/A | Comment |
| --- | --- | --- | --- | --- | --- |
| Final IP reconciliation on F-304-01 and F-304-04, every discrepancy explained |  |  |  |  |  |
| IP returned or destroyed on the sponsor's written instruction, with records |  |  |  |  |  |
| Controlled-substance IP handled under DEA requirements |  |  |  |  |  |
| Sponsor equipment returned and marked returned on F-312-01 |  |  |  |  |  |
| Temperature records for the full storage period filed (F-304-02) |  |  |  |  |  |

## Regulatory and quality (SOP-15 5.5 to 5.7)

| Item | Owner | Target | Done | N/A | Comment |
| --- | --- | --- | --- | --- | --- |
| ISF reconciled against F-204-01 and the sponsor's list; gaps filed or explained on F-306-01 |  |  |  |  |  |
| Delegation log closed with end dates |  |  |  |  |  |
| Monitor access to site systems removed (F-401-01) |  |  |  |  |  |
| Closeout QC review on F-700-01; CAPAs and F-600-02 items closed or owned |  |  |  |  |  |
| Close-out visit recorded on F-600-01; close-out letter filed |  |  |  |  |  |
| Final report to the sponsor (device: sponsor and IRB within 3 months) |  |  |  |  |  |
| IRB closure submitted; closure letter filed and copied to sponsor |  |  |  |  |  |
| Investigators reminded to update financial disclosure for 1 year after completion |  |  |  |  |  |

## Finance (SOP-15 5.8)

| Item | Owner | Target | Done | N/A | Comment |
| --- | --- | --- | --- | --- | --- |
| Payments received reconciled with work performed; final invoice sent, holdback requested |  |  |  |  |  |
| Participant payments complete, final reconciliation signed, cards closed (F-310-01) |  |  |  |  |  |
| No sponsor-paid item billed to a participant or insurer (SOP-M2, if adopted) |  |  |  |  |  |

## Archiving (SOP-15 5.9)

| Item | Owner | Target | Done | N/A | Comment |
| --- | --- | --- | --- | --- | --- |
| Records prepared for archive and recorded on F-402-01 |  |  |  |  |  |
| Sponsor told in writing of the archive location and person responsible |  |  |  |  |  |

## Records

| Close-out visit date |  | IRB closure date |  |
| --- | --- | --- | --- |
| Retention period end date or trigger (SOP-12 5.9) |  | Archive location and box IDs |  |
| ISF gaps and resolution |  | Final financial status (Finance / Contracts Lead) |  |
| Comments |  |  |  |

| Role | Printed Name | Signature | Date |
| --- | --- | --- | --- |
| Lead CRC |  |  |  |
| Finance / Contracts Lead (finance items) |  |  |  |
| Principal Investigator (closeout complete) |  |  |  |
| Principal Investigator (archive complete) |  |  |  |