# Member Site Integration Plan and Exit Checklist

Purpose: Model N only. Plans and tracks a member site's integration on a fixed timeline (day-one items and day 30, 90 and 180 gates, with the network effective date at day 90), in-flight study notices, PI-approved participant care plans, systems migration, change of ownership, study transfers and, later, its exit from the network.

Instructions

The Network Quality Lead and the site Integration Lead write the plan once the decision on F-901-01 is to proceed (SOP-N2 5.3.1). Each milestone has an owner and a target date. Write the owner in the Comment column.

Part 0 holds the per member site rows of SOP-N1 5.1.1 and is confirmed on the closing date, or on the network start date for a founding site (SOP-N2 5.1.1, 5.1.3). Gate dates run from that date (SOP-N2 5.1.2).

A missed gate is recorded in Part 8 with the reason and a new date within [DEFAULT: 5 business days] and reported to the Network Executive. A second missed gate needs a Network Executive decision, recorded in Part 8 (SOP-N2 5.1.4).

The site keeps operating under its own approved SOPs until its network effective date, target [DEFAULT: day 90]. Do not run old and new SOPs for the same process without a transition rule recorded in Part 1.

Every sponsor, IRB or CTA notice, approval or consent that must precede the change is sent or obtained before closing; where one is not, the existing contracting entity, PI, location and payee stay in place for that study until it is (SOP-N2 5.4.2).

The Network Quality Lead reviews progress at least [DEFAULT: every 2 weeks] and records each review in Part 8.

Study visits, dosing and safety follow-up must not be interrupted. The PI approves a participant care plan for each in-flight study with participants on treatment or in follow-up (Part 4).

Any transfer of PHI between legal entities needs a basis recorded on F-905-01.

Part 9 is opened when a site exits. It is closed with the Network Executive's signature.

| Member site |  | Legal entity and entity type |  | Acquisition or affiliation |  |
| --- | --- | --- | --- | --- | --- |
| Closing date |  | Site Integration Lead |  | Plan version and date |  |

## Part 0. Day-one items at the closing date (SOP-N1 5.1.1; SOP-N2 5.1.1)

| Item | Yes | No | N/A | Comment |
| --- | --- | --- | --- | --- |
| Each in-flight study has a named PI and a PI-approved participant care plan (Part 4) |  |  |  |  |
| Safety reporting route to each sponsor unchanged or confirmed in writing |  |  |  |  |
| PI coverage for absences named (SOP-16) |  |  |  |  |
| Every notice, approval or CTA consent that must precede the change sent or obtained before closing (Part 3); otherwise the existing arrangement stays |  |  |  |  |
| HIPAA basis for any PHI or records already moving to the Network Office recorded on F-905-01 |  |  |  |  |
| Controlled-substance IP held only where a DEA registration covers the location; Schedule I IP only under a Schedule I researcher registration |  |  |  |  |
| Insurance in force from the closing date; tail coverage where a claims-made policy ends |  |  |  |  |
| Site operating under its own approved SOPs until its network effective date, with any transition rule in Part 1 |  |  |  |  |

## Part 1. Plan basis

| Entity type and Appendix B assignments added to F-900-02 (date) |  | Network effective date for this site (target [DEFAULT: day 90]) |  | Transition rules (where old and new SOPs overlap) |  |
| --- | --- | --- | --- | --- | --- |
| Date network SOPs replace the site's own SOPs |  |  |  |  |  |

## Part 2. Integration gates and milestones (SOP-N2 5.1.2, 5.3)

| Item | Target date | Date closed | N/A | Comment |
| --- | --- | --- | --- | --- |
| Day 30: entity type and Appendix B assignments on F-900-02 |  |  |  |  |
| Day 30: Appendix A completed for the site's state(s) |  |  |  |  |
| Day 30: remaining sponsor and IRB notices (those not needing prior approval) sent for each in-flight study (Part 3) |  |  |  |  |
| Day 30: each critical gap from F-901-01 closed or under CAPA |  |  |  |  |
| Day 90: all site staff trained; Lean Edition core SOPs, modules SOP-M1, SOP-M2 and SOP-M5, and Network SOPs effective at the site |  |  |  |  |
| Day 90: former site SOPs retired and mapped to network SOPs (SOP-01) |  |  |  |  |
| Day 90: local addenda approved (F-900-01) |  |  |  |  |
| Day 90: contract, registration and certificate items closed or on a counsel-confirmed timeline (Part 6) |  |  |  |  |
| Day 90: systems migration plan approved (Part 5) |  |  |  |  |
| Day 180: each major gap closed (CAPA numbers in Comment) |  |  |  |  |
| Day 180: systems migration complete and verified |  |  |  |  |
| Day 180: readiness check by the Network Quality Lead; starting tier assigned (SOP-N4) |  |  |  |  |
| First central QA audit scheduled within [DEFAULT: 6 months] of integration (SOP-N4) |  |  |  |  |

## Part 3. In-flight studies and notices (SOP-N2 5.4)

| Protocol | Sponsor | PI | Participants on treatment or in follow-up | What changes (IRB, 1572, CTA entity, payee, address, contacts) | Prior approval or CTA consent needed before closing; obtained (date) | Sponsor notice (date) | IRB notice or approval (date) | New 1572 or agreement signed (date) | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Part 4. Participant care plan per in-flight study (PI-approved, SOP-N2 5.4.3)

| Protocol | Visits, dosing and safety follow-up continue on schedule | IP storage, temperature records and accountability continue; any move sponsor-approved | PI or Sub-I available; safety reporting without a gap | Participants told whom to call (IRB-approved) | PI approval (signature and date) |
| --- | --- | --- | --- | --- | --- |

## Part 5. Systems migration (SOP-N2 5.5)

| System | System Owner | Data to migrate | Verification (record counts, sample comparison) | F-905-01 entry (if PHI crosses entities) | Date complete |
| --- | --- | --- | --- | --- | --- |

## Part 6. Change of ownership (acquisitions, SOP-N2 5.6; counsel confirms each item)

| Item | Target date | Date closed | N/A | Comment |
| --- | --- | --- | --- | --- |
| CTAs and budgets: consent to assignment or change of control obtained before closing where required; novation or amendment as each requires; payee changed only after signature |  |  |  |  |
| DEA registration for each location: new registration or written DEA consent (21 CFR 1301.12; 1301.52(b)) |  |  |  |  |
| DEA transfer-of-business notice sent to the DEA Special Agent in Charge at least 14 days before closing, unless waived (21 CFR 1301.52(d)) |  |  |  |  |
| State controlled-substance registration (Appendix A); Schedule I researcher registration for each Schedule I protocol (SOP-N5 5.8.3) |  |  |  |  |
| CLIA change of ownership notice sent within 30 days of the change (42 CFR 493.39 for waiver; 493.51 for compliance; check the rule for the site's certificate type) |  |  |  |  |
| State facility, pharmacy or radiation licenses; payer enrollment if billing |  |  |  |  |
| Insurance in force from closing; tail coverage for claims-made policies |  |  |  |  |
| Records custody after closing agreed |  |  |  |  |
| 21 CFR 11.100(c) certification from the new entity where staff sign electronically |  |  |  |  |

## Part 7. Study transfer plan (SOP-N2 5.8)

| Protocol | From PI and site | To PI and site | Sponsor agreement and CTA (date) | IRB approval receiving / closure transferring (dates) | New 1572 or agreement (date) | Participant notice, re-consent and records transfer basis | IP transfer or return (chain of custody) | Last date transferring PI / first date receiving PI |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Part 8. Progress reviews and missed gates

| Review date | Gates or milestones overdue, reason and new date | Actions | Reported to Network Executive (date) and decision on a second missed gate | Reviewer |
| --- | --- | --- | --- | --- |

## Part 9. Exit checklist (SOP-N2 5.9)

| Exit reason (agreement ended, sale, closure, escalation decision) |  | Exit date |  | Exit opened by and date |  |
| --- | --- | --- | --- | --- | --- |

| Protocol | Decision (transfer, continue outside the network, close out) | Sponsor agreement (date) | Participant care continued until complete (PI initials) | Records custodian and location | F-402-01 updated (date) |
| --- | --- | --- | --- | --- | --- |

## Exit items

| Item | Yes | No | N/A | Comment |
| --- | --- | --- | --- | --- |
| Every in-flight study has a confirmed disposition before the exit date is set |  |  |  |  |
| Central services each continuing study depended on handed back to the site or replaced, with a dated handover (date and receiving person) |  |  |  |  |
| Network-signed or tri-party CTAs amended or assigned to the member entity (SOP-N2 5.9.2; SOP-N3) |  |  |  |  |
| Records in network systems exported as certified copies with audit trails, or kept under a continued-access agreement, before access is removed (SOP-N6 5.7.5) |  |  |  |  |
| Records custodian recorded on F-402-01 and sponsors told by the site Regulatory Coordinator |  |  |  |  |
| IDE studies: FDA notified within 10 working days of any custody transfer (21 CFR 812.140(e)) |  |  |  |  |
| Site staff removed from network systems and network staff removed from site systems (F-401-01), except accounts kept under a continued-access agreement |  |  |  |  |
| SOPs that apply from the exit date recorded, and staff trained on any change before the exit date (SOP-N2 5.9.4) |  |  |  |  |
| Shared staff and central investigators: delegation ended on F-302-01 unless a staffing agreement continues it, sponsor told (revised 1572 where required), F-904-01 updated, access removed (SOP-N2 5.9.4) |  |  |  |  |
| Sale of a type (a) site: SOP-N2 5.6.1 items completed for the buyer |  |  |  |  |
| Data and records kept, returned or destroyed as agreed, recorded on F-905-01; nothing within its retention period destroyed |  |  |  |  |
| Financial reconciliation complete for all studies and agreements |  |  |  |  |
| Site removed from F-900-02 |  |  |  |  |
| Exit reported at network management review |  |  |  |  |

| Role | Printed Name | Signature | Date |
| --- | --- | --- | --- |
| Network Quality Lead |  |  |  |
| Site Director |  |  |  |
| Network Executive (integration complete) |  |  |  |
| Network Executive (exit closed) |  |  |  |