# Study Activation Checklist

Purpose: Confirms that regulatory, contract, training, product and operational requirements are complete before the first participant is consented.

Instructions

The Regulatory Coordinator maintains this checklist throughout start-up. Enter the date done for each item and write the record location in the Comment column, or mark N/A with the reason.

The Lead CRC and Regulatory Coordinator review the completed checklist. The PI and Site Director sign to record that the site is ready.

No participant may be consented, and no study procedure done, until this checklist is approved and the sponsor's written activation is on file. Sponsor activation alone does not authorize the start.

After activation, use a new checklist limited to the changed items for a new PI, location or laboratory (SOP-205 5.8).

File the signed checklist in the ISF.

| Protocol number |  | Sponsor |  |
| --- | --- | --- | --- |
| PI name |  | IRB of record |  |
| Scope (initial activation, or change: new PI, location, laboratory) |  |  |  |

## Start-up

| Qualification visit date |  | Site initiation visit date |  |
| --- | --- | --- | --- |
| Reliance agreement and local requirements (ancillary review, local context) |  | Regulatory packet sent to sponsor (date) |  |

## Regulatory

| Item | Date done | N/A | Comment |
| --- | --- | --- | --- |
| IRB approval of protocol, consent form(s), recruitment and participant materials, with approval letter filed |  |  |  |
| Local IRB review, reliance agreement or institutional acknowledgment, where required |  |  |  |
| Form FDA 1572 or device investigator agreement signed, filed and sent to sponsor |  |  |  |
| Signed protocol signature page |  |  |  |
| Financial disclosures complete for all investigators listed |  |  |  |
| CVs, licenses and GCP training on file for all investigators and delegated staff |  |  |  |
| Debarment and exclusion screening current for all study staff |  |  |  |
| Delegation of Authority Log signed by the PI for all staff (F-302-01) |  |  |  |
| SIV completed and protocol and system training recorded for all delegated staff (F-103-01) |  |  |  |
| Laboratory certification and normal ranges on file |  |  |  |
| Controlled-substance IP: DEA and [STATE] controlled-substance registration covering the schedule and each storage address confirmed by the PI before the IP is received (SOP-304, 5.9.1) |  |  |  |
| IRB reportable-event categories and reporting windows for the study recorded for use with F-502-01 (SOP-502) |  |  |  |
| ISF set up and index current (F-204-01) |  |  |  |

## Contracts and finance

| Item | Date done | N/A | Comment |
| --- | --- | --- | --- |
| Clinical trial agreement and budget executed |  |  |  |
| Coverage analysis approved and billing grid set up, or no-billing short form (F-202-01) |  |  |  |
| Participant payment process set up and IRB-approved, if applicable (SOP-310) |  |  |  |
| Study set up in CTMS or tracking system and invoicing schedule entered |  |  |  |

## Operations

| Item | Date done | N/A | Comment |
| --- | --- | --- | --- |
| IP received, stored under monitored conditions and released for use; F-304-01 and F-304-02 started |  |  |  |
| Lab kits, specimen and shipping supplies received and within expiry |  |  |  |
| Study equipment available and calibrated; sponsor equipment logged (F-312-01) |  |  |  |
| EDC, IRT, eCOA, safety and laboratory portal access active for every delegated user, with own credentials (F-401-01) |  |  |  |
| Source document plan and Source Data Location List filed; source worksheets ready (SOP-306) |  |  |  |
| Emergency unblinding procedure available to the investigator (blinded studies) (SOP-305) |  |  |  |
| Blinded studies: blinded and unblinded roles named on F-302-01, each with a backup, and separation of unblinded records and IP areas in place (SOP-305) |  |  |  |
| Study QC plan approved on F-700-01 (SOP-700 5.2.1) |  |  |  |
| Study pages or trackers opened for AEs, SAEs and pregnancies (F-500-01, F-501-01, F-503-01) |  |  |  |
| Participant retention plan in place (SOP-309 5.1.1) |  |  |  |
| Record retention period for the study recorded from the CTA, sponsor instructions and regulations (SOP-402) |  |  |  |
| Recruitment plan and approved materials ready (SOP-300, F-300-02) |  |  |  |
| Staffing, space and facilities confirmed by the Site Director |  |  |  |

## Activation

| Sponsor written activation (green light) received (date) |  | Quality Lead spot-check of F-205-01 before PI approval, for the studies named in SOP-205 section 3 (date) |  |
| --- | --- | --- | --- |
| Comments |  |  |  |

| Role | Printed Name | Signature | Date |
| --- | --- | --- | --- |
| Regulatory Coordinator |  |  |  |
| Lead CRC |  |  |  |
| Principal Investigator (approves activation) |  |  |  |
| Site Director (co-approves activation) |  |  |  |